## Sheet1
| no obstacle, should process successfully in time | Gannt Chart for Project
| obstacle occurred, unexpected, required more time | First half of term : Week
| Future plans | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Tasks till week 10 | Set up development environment | bar: First half of term : Week 1 to First half of term : Week 2
Choosing template | bar: First half of term : Week 1 to First half of term : Week 2
Install necessary libs and dependencies | bar: First half of term : Week 2; First half of term : Week 5
Literature review, research | bar: First half of term : Week 2 to First half of term : Week 4
Familize with Open AI gym and NES | bar: First half of term : Week 5
Develop and test the reinforcement AI Abel | bar: First half of term : Week 5 to First half of term : Week 8
Project Design | bar: First half of term : Week 7 to First half of term : Week 8
Implement the basic behaviour : Abel | bar: First half of term : Week 7 to First half of term : Week 9
Obseve statistics with tensorboard : Abel | bar: First half of term : Week 8 to First half of term : Week 9
Prototype Document | bar: First half of term : Week 9 to First half of term : Week 10
Experiments with variables : Abel
Second Half of term : Week
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Tasks till week 20 | Develop and test DQN and preprogrammed actions | bar: Second Half of term : Week 11 to Second Half of term : Week 14
Implement the basic behaviour : Kane | bar: Second Half of term : Week 11 to Second Half of term : Week 16
Observe statistics : Kane | bar: Second Half of term : Week 15 to Second Half of term : Week 16
Experiments with variables : Kane | bar: Second Half of term : Week 16 to Second Half of term : Week 17
Compare results of both AI | bar: Second Half of term : Week 17 to Second Half of term : Week 20
Analysis and get documents and demo for Final submission | bar: Second Half of term : Week 17 to Second Half of term : Week 20
Weekly log and comments as project processes | Week 1 - 2 | Second Half of term : Week 11: No delay and no obstacle setting up environment : Anaconda, Jupyter ; Choosing template as CM3002 Kane and Abel: Ais playing game
| Week 2 - 3 | Second Half of term : Week 11: No delay and no obstacle setting up environment, Started literatures with suggested ones from templates, writing reviews and researching
| Week 3 - 4 | Second Half of term : Week 11: Kept doing the literature review on suggested literatures and making project proposal video, as well as researching about more literature
| Week 4 - 5 | Second Half of term : Week 11: Dependency error occurred, couldn’t correctly implement Stable baselines since it was not installed correctly. Using virtual environment to experiement more. Kept researching and writing reviews on literatures
| Week 5 - 6 | Second Half of term : Week 11: Started on project desgin section on document, keep on developing Abel
| Week 6 - 7 | Second Half of term : Week 11: Another error occurred on tensorflow, had to remove all and reinstall again.
| Week 7 - 8 | Second Half of term : Week 11: implementing basic behaviours like how far can mario go in screen, making training samples and see if it progresses.
| Week 8 - 9 | Second Half of term : Week 11: Observe statistics with tensorboard with all the trainings, checking to see if positive results are there
| Week 9 -10 | Second Half of term : Week 11: Logging on protoype section of document with all the results from codes for Abel
| Week 10 - 11 | Second Half of term : Week 11: Major Delays on logics for Kane, Changed main logic for Kane FSM to DQN and modified documents and coding
Week 11 - 12
Week 12 -13
Week 13 - 14
Week 14 -15
Week 15 - 16
Week 16 - 17
Week 17 - 18
Week 18 - 19
Week 19 -20